EVENT PLANNING TEMPLATE

This document is meant to serve as a resource for alumni events, reunions, anniversaries, etc. This is a general task list/timeline so use it as a guide but also realize every item may not apply to your event.

| TASK | COMPLETE BY: | DONE |
| --- | --- | --- |
| Secure Date | 4 months before event | ☐ |
| Secure VIP | 4 months before event | ☐ |
| Contact the alumni engagement team to post on the website | 4 months before event | ☐ |
| Contact the marketing team to coordinate save the date and reminder emails | 4 months before event | ☐ |
| Determine invitation list | 4 months before event | ☐ |
| Secure hotel block of rooms (courtesy block recommended) | 4 months before event | ☐ |
| Secure A/V (if not provided by venue) | 3.5 months before event | ☐ |
| Finalize budget | 3.5 months before event | ☐ |
| Secure venue | 3 months before event | ☐ |
| Save the date email | 3 months before event | ☐ |
| Save the date social media post on chapter’s social media page(s) | 3 months before event | ☐ |
| Design invitations | 3 months before event | ☐ |
| Food and beverage planning | 2.5 months before event | ☐ |
| Determine VIP call list | 2 months before event | ☐ |
| Online registration opens | 2 months before event | ☐ |
| Email reminder #1 | 6 weeks before event | ☐ |
| Program draft and speaker asks made | 6 weeks before event | ☐ |
| VIP travel accommodations/logistics (air, hotel, ground) | 6 weeks before event | ☐ |
| Secure speaker(s) bios | 5 weeks before event | ☐ |
| Secure photographer | 4 weeks before event | ☐ |
| Email reminder #2 | 3 weeks before event | ☐ |
| Program finalized and shared | 3 weeks before event | ☐ |
| Connect speakers and VIPs with local point person | 2 weeks before event | ☐ |
| Email reminder #3 | 1 week from RSVP deadline | ☐ |
| Confirm food and beverage guarantees | 1 week (see contract) | ☐ |
| Supplies to host (speaking points, roster, nametags, pen, sign in sheet, welcome) | 1 week before event | ☐ |
| Nametags and programs printed | 1 week before event | ☐ |
| Meet onsite for set up and final logistics | 1 week before event | ☐ |
| Send picture and short write-up to letusknow@pikapp.org | 2 days after event | ☐ |
| Follow up email to attendees | 1-week after event | ☐ |
| Obtain final outstanding invoices | 1-week after event | ☐ |
| Thank you card(s) to VIPs and speakers | 1-week after event | ☐ |
| Calls and check-ins with marketing and logistics teams | Monthly | ☐ |
| Pay vendors | See contract requirements | ☐ |
| Monitor registration numbers and increase efforts accordingly | Weekly | ☐ |
| Monitor room block | Weekly | ☐ |